## Commit History
Date | Commit | Author | Message | Files Changed | Insertions | Deletions
2026-08-08 17:46 | 5367c6f | jgcarti123-cyber | Scaffold FastAPI tool service - resolve_signal, validate_schema, check_dedup | 19 | 774 | 5
2026-08-07 20:28 | 3ecfc21 | jgcarti123-cyber | HIL capability confirmed with real data; lock in Python+FastAPI stack | 7 | 91 | 36
2026-08-06 19:19 | 70e37b0 | jgcarti123-cyber | Start items 6-7: test bench capabilities and compliance mapping | 4 | 62 | 5
2026-08-06 18:16 | 8df443b | jgcarti123-cyber | Start golden eval set (item 8) - two-tier, honest about trust level | 3 | 48 | 3
2026-08-06 17:55 | aaa59b1 | jgcarti123-cyber | Expand Jira traceability to 18 more features (feature-level) | 2 | 15 | 1
2026-08-06 17:18 | 2457fbe | jgcarti123-cyber | Defer Xray execution-status work - blocked on admin access, not code | 2 | 5 | 1
2026-08-06 17:03 | 57744ca | jgcarti123-cyber | Security review of credential-handling scripts before Xray API key setup | 2 | 13 | 0
2026-08-06 16:57 | b2b8d8f | jgcarti123-cyber | Add bug-detail enrichment (severity/project/due date/comments) and Xray execution status tooling | 4 | 287 | 19
2026-08-06 15:28 | c7611ee | jgcarti123-cyber | Scope dedup gate to category — regression coverage shouldn't be blocked | 4 | 12 | 5
2026-08-06 15:14 | 9909816 | jgcarti123-cyber | Live Jira data for Intrusion Alert; resolve traceability granularity gap | 5 | 63 | 23
2026-08-06 13:53 | 7858881 | jgcarti123-cyber | Add requirement traceability tooling (item 4) | 6 | 345 | 8
2026-08-06 13:39 | 3bed382 | jgcarti123-cyber | Add definition-of-done rubric; fix signal-verification gap it exposed | 5 | 71 | 21
2026-08-06 12:33 | 1b7291a | jgcarti123-cyber | Merge remote-tracking branch 'origin/main' (initial README) | 0 | 0 | 0
2026-08-06 12:33 | 8a9bb41 | jgcarti123-cyber | Add pipeline design docs and formal test case schema | 8 | 367 | 0
2026-08-06 11:48 | 74e84fc | John George | Initial commit | 1 | 2 | 0

## Roadmap - Requirements Items
Item # | Title | Status (as written in requirements.md) | Summary (first paragraph, see requirements.md for full detail)
1 | Authoritative signal ground truth | ✅ DONE (2026-08-06) | Real `.dbc` file + Master Signal Catalog, not PDF-parsed tables. - **Source files**: `Signal_Catalogs/TML_IVN_Communication_Matrix_CM_CANFD_V1.1.5_TM.dbc` (436 messages, 3,623 signals), `Signal_Catalogs/Master_Signal_Catalog_V4.4_20.8.25.xlsx` (VSS↔CAN cross-reference, 3,684 rows). - **Built artifact**: `Signal_Catalogs/unified_signal_index.json` — cross-validated index, every entry flagged `bit_position_match: true/false`. This is what Signal Resolution queries; never re-derive from the raw PDF
2 | Machine-readable test case schema | ✅ DONE (2026-08-06) | - **Built artifact**: `Schema/test_case_schema.json` — formal JSON Schema, derived empirically from 2,704 rows across the 22 existing feature files, not guessed. - **Key decisions** (see git/chat history for full reasoning): - `Environment` enum enforced (`LabCar`/`Vehicle`/`Bench`) for new rows only — 22 historical files keep their 6 inconsistent spellings, not retroactively fixed. - The two identically-named "Test Type" columns (execution method vs. validation scope) kept as-is, documented rat
3 | A "definition of done" rubric | ✅ DONE (2026-08-06) | - **Built artifact**: `Docs/definition_of_done.md` — two-tier rubric (Tier 1 hard gates, auto-checkable; Tier 2 quality checks, route to human on failure) plus a human-sign-off policy and status lifecycle (DRAFT → RELEASED / NEEDS_REVIEW / REJECTED). - **Key decisions**: dedup via exact-field match now, embeddings noted as a future upgrade; Tier 2 failures route to human review rather than auto-reject; mandatory human sign-off for Edge Case categories + low-confidence tags only (Happy Path/Negat
4 | Requirement traceability data | 🟡 LIVE DATA PULLED FOR NIO-F001, GRANULARITY GAP FOUND (2026-08-06) | - **Finding**: all 2,704 rows across all 22 existing feature files have an empty Requirement ID column — zero local traceability data exists, not a subset. Confirmed by direct count, not assumed. - **Source of truth**: Jira (team-confirmed). **Atlassian MCP connector is now set up and connected** (`jiratatamotors.atlassian.net`) — live-queried for Intrusion Alert on 2026-08-06, superseding the "no connector" status below. - **Confirmed live**: Jira is on **Xray** (Test/Test Execution/Test Set is
5 | Field/bug history feed | 🟡 ENRICHED FOR INTRUSION ALERT, INFORMATIONAL ONLY (2026-08-06) | The live Jira MCP pull for item 4 incidentally answered the base version of this — 27 closed Validation Bug issues linked to `NIF-117`. **Enriched same day, direct team ask**: each of the 27 now also carries `priority`, `severity` (Jira custom field `customfield_10854`, values A/B/C), `associated_project` (custom field `customfield_10721` — a TML sub-team/system area like "N.IO T.OS"/"N.IO Hypercube", distinct from the Jira project NIV which is constant across all of them), `due_date`, `fix_vers
6 | Test bench capability list | 🟢 SUBSTANTIALLY DONE for HIL (2026-08-07) | - **Built artifacts**: `Docs/test_bench_capabilities.md`; `HIL_Automation/hil_keyword_index.json` (parsed from team-provided `HIL_Automation/Keywords.xlsx` — the real HIL automation keyword library, 19-20 hardware modules, not inferred). - **Confirmed with real data, not just a yes/no**: HIL's CAN module (NI PXIe 8510) can inject any signal in the loaded DBC by name (`Set CANX Signals`), validate values with tolerances (`Check CANX Signal`), and inject raw/UDS frames. Separately, a dedicated **F
7 | Compliance/safety mapping | 🟡 CHECKED, BOTH OPEN (2026-08-06) | - **Built artifact**: `Docs/compliance_mapping.md`. - **Confirmed absent, not just unfound**: checked the DFMEA (no mention of "Intrusion" anywhere — it's generic TCU hardware analysis, not feature-specific) and all 5 requirement PDFs (523 pages, searched for ASIL/UNECE/R155/R156/ISO 26262/functional safety — zero matches). - **Both ASIL (ISO 26262) and UNECE R155 status**: unknown, needs the safety/compliance team — not something either agent investigation or more document search can resolve. -
8 | A golden eval set | 🟡 STARTED (2026-08-06) | - **Built artifact**: `Docs/golden_eval_set.md` — two-tier set. Tier 1 (3 cases, confirmed golden): `Test_89`/`Test_90`/`Test_91` — the only test cases matching the current schema end to end AND actually reviewed by a human across this project. Tier 2 (12 cases, candidates pending human sign-off): a reasoned scenario-diversity shortlist from Intrusion Alert's 88 historical rows, not an exhaustive permutation of every door/power-mode combination. - **Real cross-check already found**: historical S

## Roadmap - Tools Needed
Tool | Purpose | Priority
Claude tool-runner orchestration layer | Wire the Anthropic Python SDK's tool-runner up to the Scripts/service/ endpoints above so the 8-stage pipeline actually runs as an agent loop, per harness_design.md's coordinator/specialist pattern. anthropic SDK not yet installed in this environment. | Highest — now that the tool endpoints exist, this is the next concrete build step.
Service-side Jira/Xray auth | The Atlassian MCP connector used so far is session-scoped (OAuth via /mcp in an interactive terminal). A deployed service needs its own auth pattern — likely a service account + API token, not the interactive OAuth flow. Blocks /tools/jira_traceability_check, currently stubbed. | High — blocks any tool that needs live Jira/Xray access from the deployed service, not just this conversation.
Retrieval / embedding search | Once documents are indexed, fetch just the relevant slice per query instead of stuffing everything into context. Simple embedding search over indexed chunks is enough for this corpus size — no heavyweight vector DB needed. | Medium
Dedup/similarity tool | Compare a newly generated test case against Existing_TestCases/ rows and real Jira Test summaries (Traceability/requirement_traceability.json) using embedding similarity — category-scoped per guardrails.md #6 (only blocks Edge Case/User-Journey matches). Must be a deterministic tool call, not an LLM self-report. This is what closes the two unchecked_sources gaps in /tools/check_dedup above. | High — named guardrail, repeatedly flagged as the last unbuilt piece of the Coverage Checker.
HIL keyword lookup tool | Query HIL_Automation/hil_keyword_index.json for a real automation keyword given an intended action, feeding guardrails.md #11 (prefer real keywords over free-prose Gherkin). Endpoint exists at /tools/hil_keyword_lookup and currently returns 501. | Medium — new as of 2026-08-07.
Version control on the generated suite | Track diffs in the output file between pipeline runs to catch regressions. | Low, but cheap to do early.